## Summary Sheet Example
Consultant's Name
INVOICE SUMMARY SHEET
Purchase Order Number: 2000000000 | [5 empty] | Retainer Contract : 4400000000
Project Number: H.000000.0 | [5 empty] | Federal Aid Project No. :
Legacy State Project No. : 700-00-0000 | [5 empty] | Name of Project/Route :
Type of Project : | [5 empty] | Vendor Number: 310000000
Request for Payment Number : | xx / Partial or Final
PERIOD: | M/D/Y | TO | M/D/Y
|  |  |  | MAXIMUM | % | AMOUNT EARNED | PREVIOUSLY | LESS | AMOUNT DUE
|  |  |  | COMPENSATION | COMPLETE | TO DATE | INVOICED | RETAINAGE | THIS PERIOD
Task Order No. H.000000 - 2000000000 - (Description ) - Total
Consultant Legacy No. 701-65-0001 - Subtotal |  | Lump Sum |  | 75000 | 100% | 75000 | 71250 | 0 | 3750
(Notice to Procced M/D/Y) (Expiration Date M/D/Y)
Subconsultant H.000000 - 2000000000 - Subtotal |  | Lump Sum |  | 55500 | 100% | 55500 | 55500 | 0 | 0
(Notice to Proceed M/D/Y) (Expiration Date M/D/Y)
Task Order No. H.000000 - 2000000000 - (Description ) - Total
Consultant Legacy No. 701-65-0002 - Subtotal |  | Billable |  | 65450 | 100% | 65403.5 | 61472 | 3270.18 | 661.32
(Notice to Procced M/D/Y) (Expiration Date M/D/Y)
Task Order No. H.000000 - 2000000000 - (Description ) - Total
Consultant Legacy No. 701-65-0003 - Subtotal |  | Lump Sum |  | 199000 | 50% | 99500 | 0 | 4975 | 94525
(Notice to Procced M/D/Y) (Expiration Date M/D/Y)
Task Order No. H.000000 - 2000000000 - (Description ) - Total
Consultant Legacy No. 701-65-0004 - Subtotal |  | Cost Plus |  | 35250 | 65% | 22912.5 | 12000 | 1145.63 | 9766.87
(Notice to Procced M/D/Y) (Expiration Date M/D/Y)
Subconsultant H.000000 - 2000000000 - Subtotal |  | Cost Plus |  | 58160.52 | 95% | 55252.49 | 0 | 2762.62 | 52489.87
(Notice to Proceed M/D/Y) (Expiration Date M/D/Y)
Task Order No. H.000000 - 2000000000 - (Description ) - Total
Consultant Legacy No. 701-65-0005 - Subtotal |  | Lump Sum |  | 22002.45 | 5% | 1100.12 | 955 | 55.01 | 90.11
(Notice to Procced M/D/Y) (Expiration Date M/D/Y)
Total |  |  |  | 510362.97 |  | 374668.61 | 201177 | 12208.44
[6 empty] | TOTAL AMOUNT DUE THIS PERIOD: |  |  | 161283.17
Certified Correct by: |  |  |  | Contact Information Regarding Invoicing Questions:
_________________________________________ |  |  |  | Name:________________________Telephone#:_______________Email:___________________________
Principal Member's Signature