## Sheet1
Schedule for Topographic Survey and Preliminary Plans
S.P. No. 700-30-0052 (Eng.), S.P. No. 023-05-0029 (Const.), Jct. LA 1236 to Jonesboro Bypass, US 167
Calendar Days |  | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 65 | 70 | 75 | 80 | 85 | 90 | 95 | 100 | 105 | 110 | 115 | 120 | 125 | 130 | 135 | 140 | 145 | 150 | 155 | 160 | 165 | 170 | 175 | 180 | 185 | 190 | 195 | 200 | 205 | 210 | 215 | 220 | 225 | 230 | 235 | 240 | 245 | 250 | 255 | 260 | 265 | 270 | 275 | 280 | 285 | 290 | 295 | 300 | 305 | 310 | 315 | 320 | 325 | 330 | 335 | 340 | 345 | 350 | 355 | 360 | 365 | 370 | 375 | 380 | 385 | 390 | 395 | 400 | 405 | 410 | 415 | 420 | 425 | 430 | 435 | 440 | 445 | 450 | 455 | 460 | 465 | 470 | 475 | 480 | 485 | 490 | 495 | 500 | 505 | 510 | 515 | 520
Activity | Duration
NTP
Topographic Survey | 210 | bar: 5 to 210
Topo Survey Review | 5 | bar: 215
Pre-Design Conference | 5 | bar: 220
NTP
30% Preliminary Plans | 50 | bar: 225 to 270
30% Review | 20 | bar: 275 to 290
60% Preliminary Plans | 90 | bar: 275 to 360
60% Review | 20 | bar: 365 to 380
90% Preliminary Plans | 60 | bar: 365 to 420
Pre-PIH Review | 20 | bar: 425 to 440
Revise 90% Plans | 20 | bar: 445 to 460
Distribute PIH Plans | 30 | bar: 465 to 490
Plan-In-Hand Meeting | 5 | bar: 495
Revise PIH Plans | 20 | bar: 500 to 515